## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2221-swen-261-07-f-Joe'sOs
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page. | Pass | Qadira Moore; 10/24/22; There is a button on all pages that leads to the list of products | Pass | VW - 11/7/22 - EMAIL vww9966@rit.edu
| Given that I am not on the Products page when I choose the Products page then I am taken to the Products page. | Pass | Qadira Moore; 10/24/22; Products page works | Pass | VW - 11/7/22
| Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available. | Pass | Qadira Moore; 10/24/22; | Pass | VW - 11/7/22 - I think? I can't really test this
| Given that I am on the products page when there are products in the inventory then I see each product and short description. | Pass | Qadira Moore; 10/24/22; You see the product name and image and can click to see details | Pass | VW - 11/7/22 - In place of a short description I see a beautiful image
| Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart. | Pass | Qadira Moore; 10/24/22; When a product is selected there is an add to cart button | Pass | VW - 11/7/22
As a Customer, I want to type the names of donuts to immediately find them, so I can save time without browsing. | Given that I type in a nonexisting donut when I use the search feature then I expect to see a message saying nothing was found. | Pass | Qadira Moore; 10/24/22; When a non-existent product is searched for nothing appears | Fail | AN - 11/7/22 EMAIL akn1329@rit.edu, there is no message but no results are displayed either which is good
| Given that I type in an existing donut when I use the search feature then I expect to see the available donut. | Pass | Qadira Moore; 10/24/22; Links to the product details appear when searched for | Pass | AN - 11/7/22 Works perfect
As a User, I want to create an account, so that I can register my username for my login. | GIVEN I do not have an account, WHEN I try to login, or checkout, THEN I should be asked to create a new account. | Pass | Jason Berry; 10/24/22; New account is created when a new user logs in | Pass | AN - 11/7/22 Can't checkout or add to cart without an account
| GIVEN I do not have an account, WHEN I try to make an account, I should have to enter a username which is specific to my account. | Pass | Jason Berry; 10/24/22; When a new user logs in with their username a new account is created | Pass | AN - 11/7/22 Can't log in with an empty username
As a Customer, I want to log in with my username, so that I can edit my shopping cart to check out in the future. | GIVEN I have an account, WHEN I try to login, or checkout, THEN I can go to checkout. | Pass | Jason Berry; 10/24/22; A user can login and access their cart | Pass | AN - 11/7/22 Works perfect
| GIVEN I am not currently logged in, WHEN I access the homepage, THEN I should be prompted to log in. | Pass | Jason Berry; 10/24/22; When a user who is not logged in tries to add or access the cart they are asked to login | Pass | AN - 11/7/22 Homepage is the login page when not logged in
As an Admin, I want to log in with my username, so that I can have access to the admin view. | Given I have not yet signed in when I go to the home page then I expect to see an option to sign in. | Pass | Nihar Patel, 10/23/22, logging in as the admin grants access to the admin view, where before signed in there is a button for logging in as a user or admin | Pass | AN - 11/7/22 Homepage is the login page when not logged in
| Given I have signed when I go back to the home page then I expect to see access to the inventory and orders as the admin. | Pass | Nihar Patel, 10/23/22, logging in as the admin grants access to the admin view, where after signed in, the cart button disappears and an admin view appears | Pass | AN - 11/7/22 When signed in as admin, you can see and edit the inventory
As an owner I want to be able to change the price so that I can adapt to the market and alter the prices of donuts depending on supply and demand. | Given I want to change the price of a donut when I go to update a donut then I expect it to change the price of every donut in the inventory. | Pass | Nihar Patel, 10/23/22, logging in as the admin grants access to the inventory, where the admin can change the price of each donut from the inventory page or details page | Pass | AN - 11/7/22 (see VAUGHN WOERPEL for clarification)
As an owner I want to be able to change the quantity so that when a user buys something or we cook more donuts we can show the user. | Given a user buys a donut when I update the donut's quantity then I expect the quantity to update for the user too. | Pass | Nihar Patel, 10/23/22, logging in as the admin grants access to the inventory, where the admin can change the quantity of each donut from the inventory page or details page | Pass | AN - 11/7/22 Can reduce quantity of donuts by buying on user, change is visible for admin in inventory
| Given a the shop makes more donuts when I update the donut's quantity then I expect the quantity to update for the user too. | Pass |  | Pass | AN - 11/7/22 Can update quantity of donuts on admin, is visible for user
As a Customer, I want to remove items from my shopping cart, so that I don't have to buy items I no longer want. | Given I am a customer with items in my shopping cart when I click a button to remove an item then I expect my cart to be updated to show one less item. | Pass | Joe Meyer; 10/24/22; In the cart page there is an x button next to each product that removes all of the items from the cart | Pass | AN - 11/7/22 Works perfect
| Given I am a customer with items in my shopping cart when I click a button to change the number of specific donuts then I expect my cart to be updated to show less donuts. | Pass | Joe Meyer; 10/24/22; There is a plus and minus next to each product that increases or decreases the quantity of that product in the users cart | Pass | AN - 11/7/22 Works perfect
As a Customer, I want to clear my shopping cart, so that I can restart choosing which items I want. | Given I am a user with items in my cart when I click a remove all button then I expect all items to be removed from my cart. | Pass | Joe Meyer; 10/24/22; There is a clear button that removes everything from the user's cart | Pass | AN - 11/7/22 Works perfect
As a Customer, I want to add donuts from the inventory, so that I can proceed to checkout for the donuts I want. | Given I'm a customer trying to buy donuts when I find a donut I like then I expect to be able to add it to my own cart | Pass | Bryan Lee, 10/23/22; adding a donut to cart from the donut details page adds 1 of the donut selected to the cart. Either from the cart page or the donut's details page, a customer can add to cart again to increment by 1 or edit the quantity easier in the cart page. | Pass | AN - 11/7/22 Works perfect
| Given I'm a customer trying to buy donuts when I add a donut to my shopping cart then I expect to be able to see it when I access my cart | Pass | Bryan Lee, 10/23/22; properly shown in cart page when donut added to cart | Pass | AN - 11/7/22 Works perfect
As a user I want to see reviews so that I know if other people like the donut I want to purchase. | Given I am considering a product when I look for reviews then I expect to see descriptions from other users. |  |  | Pass | JM - 11/8/22
As a user I want to add reviews so that I can let other people know if the donut is good or not. | Given I have bought a product when I go to the product page then I expect to see a way to add a review. |  |  | Pass | JM - 11/8/22
As a Customer I want to pay using my credit card so that when the product arrives, I don't have to pay with cash on hand. | GIVEN that I have items in my cart and want to buy then, WHEN I checkout, THEN I expect an order description and the price. |  |  | Pass | JM - 11/8/22
| GIVEN that I have items in my cart and want to buy then, WHEN I checkout and something is no longer available, THEN I expect to see a message letting me know I cannot buy it anymore. |  |  | Pass | JM - 11/8/22; The item will just not be added to the cart
| GIVEN that I check out, WHEN I go back to the product page, THEN I expect to see the inventory updated |  |  | Pass | JM - 11/8/22
As a user I want to easily move around the site so that I do not get frustrated trying to do anything. | Given I am a user when I go to the website then I expect to be able to do anything I want easily |  |  | Pass | JM - 11/8/22; Not objective but I think most of it is easy to follow